## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1
3651912 | 68406 | ATM Project | 20 | ATM_1-20 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Balance inquiry into savings option not displaying | Initial State: In transaction type menu. Steps to reproduce: Press 4 to choose Balance Inquiry. Expected result: 1) Checking 2) Savings 3) Money Market Actual Result: 1) Checking 2) Money Market | 3 | Resolved | 3 | Normal | [6 empty] | 320109 | Jonas Wong | Jan. 26, 2022 18:43 |  | 320109 | Jonas Wong | Jan. 26, 2022 18:44 | 0 | 0
3651895 | 68406 | ATM Project | 19 | ATM_1-19 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Transferring receipt shows inverse account types. | Initial State: When either checking or savings is chosen to transfer to or from and amount to transfer screen is being displayed. Steps to reproduce: Transfer any amount of money. Expected result: If transferring from checking to savings, receipt should show "TRANSFER FROM: CHKG TO: SVGS". If transferring from savings to checking, receipt should show "TRANSFER FROM: SVGS TO: CHKG". Actual Result: If transferring from checking to savings, receipt shows "TRANSFER FROM: SVGS TO: CHKG". If transferring from savings to checking, receipt shows "TRANSFER FROM: CHKG TO: SVGS". Defect still exists in version 1.1 | 2 | In Progress | 3 | Normal | [6 empty] | 320109 | Jonas Wong | Jan. 26, 2022 18:34 |  | 320109 | Jonas Wong | Jan. 27, 2022 11:16 | 0 | 0
3651877 | 68406 | ATM Project | 18 | ATM_1-18 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Pressing invalid option causes $20.00 popup | Initial State: Machine is on with card inserted and pin entered. Anytime there are multiple number options to choose from. Steps to reproduce: Press any number on the keypad which is not one of the options. Expected result: Nothing happens. Actual Result: $20.00 popups up on the gray space of the application. | 3 | Resolved | 3 | Normal | [6 empty] | 320109 | Jonas Wong | Jan. 26, 2022 18:24 |  | 320109 | Jonas Wong | Jan. 26, 2022 18:25 | 0 | 0
3651864 | 68406 | ATM Project | 17 | ATM_1-17 | 292966 | Bug |  |  | 63856 | 1.1 | Function: Dollar sign missing before number 60 during withdrawals | Initial State: Menu of account types is being displayed. Steps to reproduce: Choose any of the 3 account types. Expected result: Third option should read: 3) $60 Actual Result: Third option reads: 3) 60 | 1 | Open | 3 | Normal | [6 empty] | 320109 | Jonas Wong | Jan. 26, 2022 18:15 |  | 320109 | Jonas Wong | Jan. 26, 2022 18:15 | 0 | 0
3649554 | 68406 | ATM Project | 16 | ATM_1-16 | 292966 | Bug |  |  | 63856 | 1.1 | Function: Transfer from Checking to Savings | Initial State: Logged in on card 2 Steps to Recreate: 1. Transfer any valid amount from checking to savings Expected Result: System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) Actual Result: System displays an invalid account type error message | 1 | Open | 3 | Normal | [6 empty] | 319975 | LAB1-34 | Jan. 25, 2022 20:52 |  | 319975 | LAB1-34 | Jan. 25, 2022 20:52 | 0 | 0
3649515 | 68406 | ATM Project | 15 | ATM_1-15 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Any transaction (Found in MFT) | Initial State: Logged in with card 1 Steps to reproduce: 1. Complete any transaction Expected Result: Receipt should show correct transaction information Actual Result: Receipt shows incorrect card number (Bug present in version 1.1) | 2 | In Progress | 3 | Normal | [6 empty] | 319975 | LAB1-34 | Jan. 25, 2022 20:42 |  | 319975 | LAB1-34 | Jan. 25, 2022 20:49 | 0 | 0
3649507 | 68406 | ATM Project | 14 | ATM_1-14 | 292966 | Bug |  |  | 63856 | 1.1 | Function: Balance Inquiry into Savings | Initial State: In the Balance Inquiry menu as Card Number 1 Step to reproduce the bug: Select the Savings Account Option Expected Outcome: Output the balance of the Savings account under Card Number 1 Actual Outcome: Outputted "Unknown Error" and withdrew $500.00 | 1 | Open | 3 | Normal | [6 empty] | 319975 | LAB1-34 | Jan. 25, 2022 20:41 |  | 319975 | LAB1-34 | Jan. 25, 2022 20:41 | 0 | 0
3649485 | 68406 | ATM Project | 13 | ATM_1-13 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Spelling mistake in cancelled transaction message (Found in MFT) | Initial State: Logged in with card 1 Steps to Reproduce: 1. Select any transaction 2. Cancel the transaction before completion Expected Outcome: Message should read: "Last transaction was cancelled Would you like to try again?" Actual Outcome: "Last transaction was cancelled Wood you like to try again?" | 3 | Resolved | 3 | Normal | [6 empty] | 319975 | LAB1-34 | Jan. 25, 2022 20:35 |  | 319975 | LAB1-34 | Jan. 25, 2022 20:51 | 0 | 0
3645881 | 68406 | ATM Project | 11 | ATM_1-11 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Re-entering PIN after entering the wrong pin (ALSO FOUND IN MFT) | Initial State: System is on but not logged in to any account Steps to reproduce bug: 1. Enter any card number 2. Provide the wrong PIN1 or 2 times 3. Provide the correct PIN Expected outcome: After entering the correct PIN, it proceeds to the main menu Actual outcome: After entering the correct PIN, it asks the user to enter the pin again. No matter how many times the incorrect PIN is entered, when the correct PIN is entered, the display will still ask the user to enter PIN again. | 2 | In Progress | 3 | Normal | [6 empty] | 319975 | LAB1-34 | Jan. 24, 2022 21:19 |  | 319977 | Mathew Pelletier | Jan. 25, 2022 20:52 | 0 | 0 | Jan. 25, 2022 20:52 Mathew Pelletier issue still exists in version 1.1
3645857 | 68406 | ATM Project | 10 | ATM_1-10 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Inserting card 3 causes system to lockup | Initial state: System running not in use by customer Steps to reproduce: Click insert card Enter 3 for card number Enter any pin number Expected result Card is rejected Actual result System locks up and no longer accepts inputs | 3 | Resolved | 3 | Normal | [6 empty] | 319977 | Mathew Pelletier | Jan. 24, 2022 21:12 |  | 319977 | Mathew Pelletier | Jan. 27, 2022 10:42 | 0 | 0
3645779 | 68406 | ATM Project | 9 | ATM_1-9 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Balance Inquiry into Money Market with Card Number 2 | Initial State: Logged in as Card Number 2 Steps to reproduce bug: 1. Navigate to Balance Inquiry 2. Select Money Market account Expected Outcome: Displays the balance of Money Market account in the log. Card Number 2 has a money market account. Actual Outcome: Displays "invalid account type". | 3 | Resolved | 3 | Normal | [6 empty] | 319975 | LAB1-34 | Jan. 24, 2022 21:02 |  | 319977 | Mathew Pelletier | Jan. 25, 2022 20:51 | 0 | 0
3645717 | 68406 | ATM Project | 8 | ATM_1-8 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Transfer function moving incorrect amounts (Also found in MFT) | Initial state: Logged in with card 1 Steps to reproduce: Select transfer Select an account to transfer from Select a different account to transfer to Select an amount to transfer Expected Results: Selected amount moved from one account to the other Actual results" Selected amount - $0.50 transferred | 3 | Resolved | 3 | Normal | [6 empty] | 319977 | Mathew Pelletier | Jan. 24, 2022 20:53 |  | 319977 | Mathew Pelletier | Jan. 25, 2022 20:50 | 0 | 0
3645713 | 68406 | ATM Project | 7 | ATM_1-7 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Displaying "insufficient cash available" message | Initial State: Logged in as Card Number 1 with $0.00 in the machine Steps to reproduce bug: 1. Navigate to Withdrawals 2. Choose Savings or Checking account 3. Choose any valid option Expected outcome: Displays a message, "Insufficient cash available" Actual outcome: Displays a message, "Insuficient cash available" (There is a typo) | 2 | In Progress | 3 | Normal | [6 empty] | 319975 | LAB1-34 | Jan. 24, 2022 20:52 |  | 319977 | Mathew Pelletier | Jan. 27, 2022 10:42 | 0 | 0 | Jan. 25, 2022 20:48 Mathew Pelletier Defect still exists in version 1.1
3645701 | 68406 | ATM Project | 6 | ATM_1-6 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Pressing invalid withdrawal amount from Savings account | Initial State: Logged in as Card Number 1 with $0 in the machine Steps to reproduce bug: 1. Navigate to Withdrawals 2. Choose Savings 3. Press any invalid option (6, 7, 8, 9, 0) Expected Outcome: Either do nothing or indicate "invalid option" Actual Outcome: Withdraws $20.00 and remains on the same menu. | 2 | In Progress | 3 | Normal | [6 empty] | 319975 | LAB1-34 | Jan. 24, 2022 20:48 |  | 319977 | Mathew Pelletier | Jan. 25, 2022 20:46 | 0 | 0 | Jan. 25, 2022 20:46 Mathew Pelletier Defect still exists in version 1.1
3645691 | 68406 | ATM Project | 5 | ATM_1-5 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Depositing less than expected (Also found in MFT) | Initial state: Logged in with card 1 Steps to reproduce: Select deposit Enter any amount to be deposited Expected result: The entered value is deposited and the total balance is updated accordingly Actual result: The entered value - $10 is deposited and the total balance reflects this | 2 | In Progress | 3 | Normal | [6 empty] | 319977 | Mathew Pelletier | Jan. 24, 2022 20:47 |  | 319977 | Mathew Pelletier | Jan. 25, 2022 20:43 | 0 | 0 | Jan. 25, 2022 20:43 Mathew Pelletier Defect still exists in version 1.1, now depositing $0.10 less than requested
3645627 | 68406 | ATM Project | 3 | ATM_1-3 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Withdrawing incorrect amounts | Expanded Upon During MST Stage: 2022-01-25 Log does not show message to bank and approval information. Initial state: Logged in with card 1 Steps to reproduce: Select withdrawal Select any account Select any $ value Expected Outcome: Withdrawal of selected $ value and corresponding new balance, log shows correct corresponding new balance and shows message to bank and approval information. Actual Outcome: Withdrawal of the next higher $ value from the menu and a corresponding balance, log shows correct corresponding new balance from higher $ value and shows message to bank and approval information. | 3 | Resolved | 3 | Normal | [6 empty] | 319977 | Mathew Pelletier | Jan. 24, 2022 20:33 |  | 319977 | Mathew Pelletier | Jan. 27, 2022 10:55 | 0 | 0
3645598 | 68406 | ATM Project | 2 | ATM_1-2 | 292966 | Bug | 92579 | User | 63855 | 1.0 | Function: Viewing savings account inquiry | Was unable to access the balance inquiry for the savings accounts. Initial state System was logged in and with card 1 Steps to reproduce: Selected account inquiry and savings account option was not present. Expected: option to select savings account inquiry. Outcome: no option for savings was present in account inquiry | 3 | Resolved | 3 | Normal | [6 empty] | 319977 | Mathew Pelletier | Jan. 24, 2022 20:25 |  | 319977 | Mathew Pelletier | Jan. 25, 2022 20:35 | 0 | 0
3645596 | 68406 | ATM Project | 1 | ATM_1-1 | 292966 | Bug |  |  | 63855 | 1.0 | Function: Balance Inquiry into Money Market with Card Number 1 | Initial State: System is on and logged in using Card Number 42 Steps to Reproduce Bug: 1. Press 4 to navigate to Balance Inquiry 2. Press 2 to check the balance of Money Market account. Expected Outcome: It should have displayed "Invalid Account Type" Actual Outcome: It displays "Unknown error" on the green screen and withdraws $500. | 3 | Resolved | 3 | Normal | [6 empty] | 319975 | LAB1-34 | Jan. 24, 2022 20:23 |  | 319977 | Mathew Pelletier | Jan. 25, 2022 20:35 | 0 | 0